## SIT-Entry-Criteria
Readiness Area | Entry Criteria | Owner/Responsible | Traget Date | Status | Comments/Remarks/Notes
People | All workstream testers are identifies | Test Team/Test Manager | 2026-02-28 | Complete
People | Testing team member as POC are designated for respective workstream | Test Lead | 2026-03-10 | Complete
People | Testers access to workstream specific application. | Test Lead/Test Team/Workstream Dev | 2026-03-10 | Complete
People | Support team member to testing team are identified ( E.g. Development, Deployment,3rd Party Partners,Business) | Workstream Dev Lead/ Third Party Vendors | 2026-03-10 | Complete
Documentation | Test Cases are prepared,reviewed/signed off | Test Team/Dev Team/ Business People | 2026-03-16 | InProgress | #. Will Completing Test Cases review by 15th March EOD
Documentation | Signed off Test Cases are uploaded in JIRA /ADO for execution | Test Team | 2026-03-18 | To Do
Documentation | Approved Requirements are uploaded in JIRA and Traceablity Established | Test Team | 2026-03-20 | InProgress
Documentation | Test Data Required for Test Cases and data dependencies identified | Test Team | 2026-03-22 | InProgress
Environment | Application Setup, Code, Configs,Integrations are deployed and fully integrated with SIT environemnt | Workstream Dev Lead | 2026-03-23 | InProgress
Environment | User Role and permisson must be defined and deployed in SIT Environment | Dev Team | 2026-03-25 | InProgress
Data | Data Conversion Activity | Conversion Lead | 2026-03-29 | InProgress
Process | Smoke Test Checklist identified and Executed before SIT Starts | Workstream Testers | 2026-03-31 | InProgress
Note:- SIT Phase 01 TimeLine : 1-April-2026 to 29-May-2026
Test Cases: 1000

## SIT-Exit-Criteria
Process Area | Exit Criteria | Owner/Responsible | Target Data | Status | Remarks
Process | Overall 90% or more test cases execution | Test Team | 2026-05-29 | Complete | Overall 98% execution
Process | Overall 95% or more pass rate | Test Team | 2026-05-29 | Complete | Overall 96% execution
Process | Severity 1(Critical) defect closed | Workstream Teams/ Development Test | 2026-05-29 | InProgress | 3-Open Critical defects Defect id: 24680, Defect id: 13570, Defect id: 22440
Process | Severity 2(High) defects closed 90% | Workstream Teams | 2026-05-29 | Complete | 95% defects has been closed
Process | Severity 3,4 (Medium,Low)can be moved to next phase after triage and closure plan | Workstream Teams | 2026-05-31 | Yet to decide | Decision Pending

## SIT-Execution-Summary
Workstream | Test Cases | Executed | Executed % | Pass | Pass % | Failed | Fail% | Blocked | Blocked %
ABC | 901 | 823 | 90% | 793 | 96% | 30 | 4% | 78 | 9%
Overall | 901 | 823 | 90% | 793 | 96% | 30 | 4% | 78 | 9%